## Code Bug Rates
Milestone | (Multiple Items)
Ship Vehicle | All
Issue Type | Code Bug
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
Values
Row Labels | # Bugs Closed Rate | # Bugs Opened Rate | # Bugs Resolved Rate
Week ending February 19 | 48 | 66 | 48
(M3 Start) Week ending March 05 | 9 | 67 | 53
Week ending March 12 | 21 | 41 | 30
Week ending March 19 | 10 | 78 | 51
Week ending March 26 | 18 | 75 | 57
Week ending April 02 | 31 | 140 | 46
Week ending April 09 | 39 | 79 | 63
Week ending April 16 | 60 | 119 | 142
Week ending April 23 | 45 | 253 | 121
Week ending April 30 | 112 | 423 | 335
Week ending May 07 | 116 | 331 | 312
Week ending May 14 | 298 | 340 | 384
Week ending May 21 | 281 | 287 | 325
Week ending May 28 | 241 | 319 | 341
Week ending June 04 | 372 | 247 | 265
Week ending June 11 | 278 | 399 | 347
Week ending June 18 | 320 | 366 | 344
Week ending June 25 | 459 | 526 | 492
Week ending July 02 | 363 | 300 | 396

## By Issue Type
Ship Vehicle | All
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
Milestone | M3
Row Labels | Count of Active Bugs
Code Bug | 315
Content Bug | 14
Doc Bug | 10
Production Issue | 28
Spec Bug | 30
Test Bug | 99

## By Severity
Ship Vehicle | All
Issue Type | Code Bug
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
Milestone | (Multiple Items)
Severity | Count of Active Code Bugs
1 | 36
2 | 220
3 | 56
4 | 3
0

## By Priority
Ship Vehicle | All
Issue Type | Code Bug
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
Row Labels | Count of Active Code Bugs
1 | 95
2 | 579
3 | 274
Unknown | 13
0

## Resolved Code Bugs by Disc
Milestone | (Multiple Items)
Ship Vehicle | All
Issue Type | Code Bug
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
# Bugs Resolved Rate | Column Labels
Row Labels | Dev | Test | PM
(M2 Start) Week ending October 02 | 6
Week ending October 09 | 40 | 6
Week ending October 16 | 10 | 2 | 2
Week ending October 23 | 10 | 1
Week ending October 30 | 31 | 2
Week ending November 06 | 78 | 4
Week ending November 13 | 251 | 3 | 4
Week ending November 20 | 227 | 11 | 9
Week ending November 27 | 55 | 3
Week ending December 04 | 154 | 6 | 3
Week ending December 11 | 174 | 20 | 5
Week ending December 18 | 193 | 9 | 12
Week ending December 25 | 47 | 8 | 2
Week ending January 01 | 15 | 1
Week ending January 08 | 117 | 15 | 7
Week ending January 15 | 175 | 14 | 6
Week ending January 22 | 162 | 18 | 3
Week ending January 29 | 154 | 15 | 5
Week ending February 05 | 189 | 15 | 4
Week ending February 12 | 70 | 3 | 1
Week ending February 19 | 40 | 1 | 6
Week ending February 26 | 60 | 4 | 4
(M3 Start) Week ending March 05 | 45 | 4 | 2
Week ending March 12 | 24 | 2
Week ending March 19 | 43 | 2 | 1
Week ending March 26 | 46 |  | 1
Week ending April 02 | 35 | 2 | 2
Week ending April 09 | 50 | 5 | 1
Week ending April 16 | 118 | 7 | 6
Week ending April 23 | 77 | 4 | 24
Week ending April 30 | 276 | 8 | 33
Week ending May 07 | 233 | 15 | 33
Week ending May 14 | 262 | 20 | 36
Week ending May 21 | 267 | 7 | 10
Week ending May 28 | 230 | 35 | 33
Week ending June 04 | 195 | 14 | 13
Week ending June 11 | 263 | 17 | 20
Week ending June 18 | 251 | 18 | 18
Week ending June 25 | 386 | 36 | 16
Week ending July 02 | 290 | 20 | 30

## Resolved Code Bug Rates
Milestone | (Multiple Items)
Ship Vehicle | All
Issue Type | Code Bug
Resolved By Organization.Org Hierarchy | (Multiple Items)
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
# Bugs Resolved Rate | Column Labels
Row Labels | By Design | Duplicate | External | Fixed | Not Repro | Won't Fix
(M2 Start) Week ending October 02 | 1 | 2 |  | 3
Week ending October 09 | 1 | 5 |  | 2 |  | 38
Week ending October 16 |  |  | 1 | 11 | 1 | 1
Week ending October 23 | 1 |  |  | 8 | 1 | 1
Week ending October 30 | 2 | 1 |  | 23 | 3 | 4
Week ending November 06 | 2 |  |  | 77 | 3
Week ending November 13 | 12 | 9 | 1 | 221 | 8 | 7
Week ending November 20 | 13 | 10 | 2 | 203 | 12 | 7
Week ending November 27 | 2 | 1 | 1 | 47 | 5 | 2
Week ending December 04 | 7 | 4 | 3 | 124 | 12 | 13
Week ending December 11 | 19 | 10 | 10 | 141 | 8 | 11
Week ending December 18 | 19 | 13 | 7 | 146 | 15 | 14
Week ending December 25 | 1 | 3 | 2 | 40 | 4 | 7
Week ending January 01 | 1 |  |  | 13 | 1 | 1
Week ending January 08 | 11 | 14 | 4 | 77 | 11 | 22
Week ending January 15 | 29 | 4 | 3 | 127 | 17 | 16
Week ending January 22 | 11 | 5 | 5 | 132 | 13 | 17
Week ending January 29 | 12 | 12 | 12 | 108 | 15 | 15
Week ending February 05 | 21 | 19 | 9 | 127 | 14 | 18
Week ending February 12 | 7 | 2 | 1 | 51 | 4 | 9
Week ending February 19 | 1 | 1 | 1 | 39 | 4 | 2
Week ending February 26 | 2 | 1 | 2 | 56 | 1 | 6
(M3 Start) Week ending March 05 | 4 | 1 | 7 | 30 | 3 | 6
Week ending March 12 | 2 | 4 | 2 | 12 | 3 | 3
Week ending March 19 |  | 2 | 1 | 40 | 1 | 2
Week ending March 26 | 2 | 1 |  | 37 | 2 | 5
Week ending April 02 | 8 | 1 | 1 | 24 | 2 | 3
Week ending April 09 | 1 | 1 | 1 | 44 | 6 | 4
Week ending April 16 | 5 | 3 | 4 | 104 | 3 | 12
Week ending April 23 | 4 | 2 |  | 94 | 3 | 2
Week ending April 30 | 18 | 8 | 6 | 251 | 8 | 26
Week ending May 07 | 21 | 26 | 4 | 191 | 22 | 17
Week ending May 14 | 28 | 9 | 4 | 242 | 14 | 21
Week ending May 21 | 10 | 19 | 6 | 204 | 20 | 25
Week ending May 28 | 14 | 28 | 15 | 204 | 15 | 22
Week ending June 04 | 19 | 20 | 8 | 154 | 10 | 11
Week ending June 11 | 8 | 21 | 4 | 232 | 15 | 20
Week ending June 18 | 23 | 26 | 7 | 202 | 14 | 15
Week ending June 25 | 33 | 43 | 9 | 296 | 36 | 21
Week ending July 02 | 20 | 36 | 8 | 227 | 35 | 15

## Bug Age
Milestone | (Multiple Items)
Ship Vehicle | All
Issue Type | Code Bug
CompCentral Path Hierarchy | APPS-App Store and Metadata Services
Bug Count
6317