## Master
Capability |  |  | Engineering Status |  |  | Service Status | [11 empty] | How Are We Landing? |  | Comments
Scope | Area | Scenarios | Status | Expected by | Doc Owner | Operational Plan | Support Enabled | Office | Office - OD\Low Activity | Skype | WDG | WDG - OD\Low Activity | State | Blocker to Extend? |  | Comment | Active Bugs | Data Views to Judge Health | Any Notable Spikes in Bugs/ICMs
[8 empty] | All Cultures: 07-Feb-2020 | All Cultures: 14-Feb-2020 | All Cultures: 7-Feb-2020 | All Cultures: 28-Feb-2020 | All Cultures: 28-Feb-2020
SW | Config | Enabling DTT Workflows | Prod Ready | 2019-10-01 | Antoine | Plan | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Config | Culture Mapping | Prod Ready | 2019-10-01 | Antoine | Plan | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Config | Cost Models | Prod Ready | 2019-10-01 | Antoine | Plan | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  |  | Need to engage with Moravia on this
SW | Job Management | DTT API authentication for Suppliers (external calls) | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Job Management | File Service API authentication for Suppliers (external calls) | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Job Properties | Pending Approval | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  |  | Validated twice in Nov
SW | Job Properties | Quality level | Prod Ready | 2019-10-01 | Antoine & Manuela | Documentation | Yes | 2020-02-01 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 | Rolled out to Translation Service on Feb 1st. Manuela to document the Quality review process
SW | Job Properties | Wordcounts (Cost Models) | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2020-02-28 |  | 2020-02-07 | 2020-02-28 |  | In Progress | 0 | 1 | Compare Wordcounts
SW | Job Properties | Status Flow (New, Claimed, Returned) | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Job Properties | PartnerId (Job routing) | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | No Job, Automated Release - Main Cultures (DTP true - Validation Pass) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | No Job, No Op. - Upon Unblocking Resources (DTP true - Validation Pass) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | No Job, Automated Release - Variant Cultures (TRAP 7 - Validation Pass) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | No Job, No Op. - Variant Cultures (TRAP 7 - Validation Pass) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | Translate Job, Upon Build Import - Main Cultures (DTP False) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | Translate Job, Upon Unblocking resources - Main Cultures (DTP False) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  |  | Active Bug with un-deleted resources | Bug - 3846257 - [DTTExport] Unblocked resources that are undeleted in a BuildImport are not DTTExported
SW | Translation | Adaptation Job, Upon Build Import - Variant Cultures (TRAP 3) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  |  | Still need to test with Skype (which has more VCs)
SW | Translation | Adaptation Job, Upon Job Return - Variant Cultures (TRAP 3) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Translation | Adaptation Job, Upon Unblocking resources - Variant Cultures (TRAP3) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2020-02-28 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | In Progress | 0 | 1 | Bugs being looked at fund after testing this scenario
SW | Validation | Review Job, Upon Locver Validation (v1) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Validation | Review Job, Upon Unblocking resources - Main Cultures (DTP true - Validation Fail) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Corner Case - Tested by SWE | 0 |  | Not validated as corner case (typically DTP=true already has a very high quality of localization)
SW | Validation | Review Job, Upon Unblocking resources - Variant Cultures (TRAP 7 - Validation Fail) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Corner Case - Tested by SWE | 0 |  | Not validated as corner case (typically DTP=true already has a very high quality of localization)
SW | Validation | Review jobs have Locver errors (v1) | Prod Ready | 2019-10-01 | Antoine | Automated | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  |  | Validated
SW | Job Management | DTT API authentication, integration in Suppliers loc process | Prod Ready | 2019-10-10 | Antoine | Documentation | n/a | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Job Management | File Service API authentication, integration in Suppliers loc process | Prod Ready | 2019-10-10 | Antoine | Documentation | n/a | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Config | Suppliers (Routing, TAT, Quality) | Prod Ready | 2019-11-15 | Antoine | Plan | n/a | 2020-03-02 | 2020-03-15 | 2020-03-15 | 2020-03-15 | 2020-03-15 | In Progress |  |  | Can route to Engineering from Mar 2nd
SW | Job Properties | Priority (Due Date) | Prod Ready | 2019-11-25 | Antoine | Documentation | Yes | 2020-02-07 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 | Bug fixed | Bug - 3889005 - Submit-MRFDirectToTranslatorExportUsingRqf failing to create job even though query returns results
SW | Validation | No Job, Upon Job Return - Review job only (Policheck and OSLEBot False Positives) | Prod Ready | 2020-01-15 | Antoine | Automated | Yes | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Validation | Review jobs have Policheck errors | Prod Ready | 2020-01-15 | Antoine | Automated | Yes | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 |  | ICM - 171426896 - Office DTT - huge number of Policheck review files for 3 languges
[5 empty] | Antoine | Automated | [10 empty] | Bug - 3900195 - [DTT] Validation Workflow ignores Policheck false positives
[5 empty] | Antoine | Automated | [10 empty] | Bug - 3901315 - Fabric Validation workflow: Monthly policheck run repeatedly creates new jobs because time stamp may not get set for up to 5 days
[5 empty] | Antoine | Automated | [10 empty] | Bug - 24713170 - OnePolicheck mismatches from Fabric Office subscription
[5 empty] | Antoine | Automated | [10 empty] | Bug - 24734263 - SVS returns Null Policheck ExclusionId for known false postive in Fabric Office Subscription
[5 empty] | Antoine | Automated | [10 empty] | Bug - 24711715 - SVS returns One Policheck action context as an hex ascii encoded string "-2D" instead of using the dash character
SW | Validation | Review jobs - Policheck with SVS - Full run of Policheck (staggered) | Prod Ready | 2020-01-15 | Antoine | Automated | n/a | 2020-02-28 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | In Progress |  | 0
SW | Validation | Review jobs have OSLEBot errors - includes Branding (v1) | Prod Ready | 2020-01-08 | Antoine | Automated | Yes | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 |  | ICM - 170940279 - Office DTT - Review jobs not created for Cerberus issues
[5 empty] | Antoine | Automated | [10 empty] | ICM - 171402658 - Office DTT - Cerberus and Policheck message format not readable
[5 empty] | Antoine | Automated | [10 empty] | ICM - 171386670 - Office DTT - Cerberus review job doesn't contain translation
[5 empty] | Antoine | Automated | [10 empty] | ICM - 3898957 - Review job created for OSLEBot failure even though translation has null TRAP value(Translation job still at supplier)
[5 empty] | Antoine | Automated | [10 empty] | Bug - 3898957 - DTT Review job created for OSLEBot failure even though translation has null TRAP value(Translation job still at supplier)
SW | Validation | Engineering Job, Upon Job Return - Review job only (Locver False Positives) | Prod Ready | 2020-01-15 | Antoine | Automated | n/a | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Validation | Review jobs have Policheck errors with SVS Hashid | Prod Ready | 2020-02-13 | Antoine | Automated | Yes | 2020-02-21 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | -1
SW | Validation | Review jobs have OSLEBot errors with SVS Hashid - includes Branding (v1) | Prod Ready | 2020-02-13 | Antoine | Automated | yes | 2020-02-21 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | -1
SW | Validation | Strings validated & exported - Review \ Engineering Jobs with False Positives | Prod Ready | 2020-02-01 | Antoine | Automated | Yes | 2020-02-07 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 0 | Workaround (using WIMS) until Mark updates his Dashboard. Also need SWE to update the Policheck cmdlet
SW | Quality | Improvement Job, Upon Translation Fix (WebUI) | Prod Ready | 2020-01-13 | Oonagh | Plan | n/a | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 |  | ICM - 169802624 - [[DTTExportWF] All failures] Execution_StorageName [Failed_DoNotRetry_DirectToTranslator-Export] is unhealthy.
SW | Quality | Improvement Job, Upon Terminology Review (WebUI) | Prod Ready | 2020-01-13 | Oonagh | Plan | n/a | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Quality | Improvement Job, Upon Consistency Review (WebUI) | Prod Ready | 2020-01-13 | Oonagh | Plan | n/a | 2020-02-07 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Quality | Improvement Job Cmdlet work (Upon Translation Fix/Terminology Review/Consistency Review) | Prod Ready | 2020-01-13 | Oonagh | Plan | Yes | 2020-01-31 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 |  | ICM - 169802624 - [[DTTExportWF] All failures] Execution_StorageName [Failed_DoNotRetry_DirectToTranslator-Export] is unhealthy.
SW | Risk Management | Builds with high level of churn are paused (and eventually un-paused) | Prod Ready | 2020-01-13 | Mark | Plan | No | 2020-02-07 | 2020-02-17 | 2020-02-17 | 2020-02-10 | 2020-02-10 | Operationalized |  | 1 | Does not cover TDBuild | ICM - 172007049 - No ICM created for spike in new wordcount for SPORel:spclient
SW | Validation | Review jobs have Locver errors with SVS Hashid | In Test | 2020-02-21 | Antoine | Automated | n/a | 2020-02-21 | 2020-02-21 | 2020-02-21 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Data | No latency for data warehouse access | Prod Ready | 2020-01-27 | n/a | Automated | Yes | 2020-02-07 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Validation | Review Job, Upon Build Import - Main Cultures (DTP true - Validation Fail) (v2) | In Dev | 2020-05-04 | Antoine | Automated | No | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Validation | Review Job, Upon Build Import - Variant Cultures (TRAP 7 - Validation Fail) (v2) | Not Started | 2020-05-04 | Antoine | Automated | No | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Validation | Review Job, Upon Job Return - Any job type but Review job (Validation Fail) (v2) | In Dev | 2020-05-04 | Antoine | Automated | No | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Validation | Engineering Job, Upon Job Return - Review job only (Validation Fail) (v2) | In Dev | 2020-05-04 | Antoine | Automated | No | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Validation | Review jobs have OneTerm errors with SVS Hashid (v2) | Not Started | 2020-04-06 | Antoine | Automated | No | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Data | Allow suppliers to send productivity data when returning jobs | Not Started | 2020-04-06 | Craig | Documentation | n/a | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Data | Reports for Productivity data | Not Started | 2020-04-06 | Ger | Documentation | n/a | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Data | High vs Standard quality criteria are met | Not Started | 2020-04-06 | Ger | Plan | No | 2020-04-17 | 2020-04-24 | 2020-04-17 | 2020-04-24 | 2020-04-24 | Waiting for it to be ready
SW | Validation | SVS API authentication (external calls) | In Test | 2020-02-21 | Dag | Documentation | No | TBD | TBD | TBD | TBD | TBD | Date - TBD
SW | Validation | SVS API authentication, integration in their loc process | In Test | 2020-02-21 | Dag | Documentation | No | TBD | TBD | TBD | TBD | TBD | Date - TBD
SW | Risk Management | No job created when Support team triggers a workflow with cmdlet | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2020-02-07 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1
SW | Risk Management | Job created when Support team triggers a workflow with cmdlet (EnableExportDTT override) | Prod Ready | 2019-10-01 | Antoine | Documentation | Yes | 2020-02-07 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized |  | 1 |  | ICM - 171556106 - [[DTTExportWF] All failures] Execution_StorageName [Failed_DoNotRetry_DirectToTranslator-Export] is unhealthy.
Bug - 3902539 - [DTTImport] Manually exported jobs on an OnDeamnd tenant (OMainCCRel) fail import a number of times before finally succeeding
SW | Risk Management | Jobs with Adjusted wordcounts over threshold are paused (and eventually un-paused) | Prod Ready | 2019-10-01 | Mark | Plan | Yes | 2019-12-18 | 2020-02-14 | 2020-02-07 | 2020-02-28 | 2020-02-28 | Operationalized
SW | Data | TAT for each job type is met (include urgent job) | In Test | TBC | Mieko | Plan | n/a | 2020-02-28 | TBD | TBD | TBD | TBD | In Progress |  |  | Dashboard did not help with recent query on TAT for Skype files
SW | Suppliers Comms | VCQs: GCS alias, Mail2Bug and bug template | No SWE Ask | n/a | Tony | Plan | n/a | 2020-02-28 | TBD | TBD | TBD | TBD | In Progress
SW | Binaries | Queries in Notification WF | No SWE Ask | n/a | Ger | Documentation | Yes | 2020-02-28 | 2019-10-01 | TBD | TBD | TBD | In Progress |  |  | Dialogs, Accelerators, Icons\images - make change v no change based on queries\notifications\bugs
SW | Binaries | Mail2Bug or MS Flow and bug template | No SWE Ask | n/a | Ger | Documentation | n/a | 2020-02-07 | 2020-01-31 | TBD | TBD | TBD | Operationalized |  | 1
SW | Translation | Styleguides and glossaries are available to suppliers | No SWE Ask | n/a | Manuela & Oonagh | Documentation | n/a | TBD | TBD | TBD | TBD | TBD | In Progress |  |  | Not urgent
SW | Risk Management | Identify resources that were not automatically sent to the suppliers | No SWE Ask | 2020-02-28 | Mark | Documentation | No | 2020-02-28 | 2020-02-14 | 2020-02-07 | 2020-02-07 | 2020-03-01 | In Progress |  | 1
SW | Support | Telemetry to identify DTT workflow failures | No SWE Ask | 2019-11-30 | Mark/Yun | Automated | Yes | 2019-12-18 | 2019-11-30 | 2019-11-30 | 2019-11-30 | 2019-11-30 | Operationalized
Note on J11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need a decision on the warehouse
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need a decision on the warehouse
Note on C13: Antoine Marti: Only have 1 Partner Id per tenant so far Tested on different slices
Note on C20: Antoine Marti: A bunch of scenarios here: Parent culture is en-us Parent culture is DTP true Variant Culture is EOL Expansion
Note on I68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated WF available 22nd Jan

## Content MVP
Moved to https://microsoft.sharepoint.com/teams/Office_GSX/Specs/Loc%20360/Documentation%20-%20Presentations/DTT%20Scenarios%20Content.xlsx?web=1

## SW Tenants
State | Office | Skype & Office | Office - On Demand | Office - Free Flow | WDG Free-Flow | WDG Free-Flow | WDG - Free-Flow | WDG - Free-Flow | Xbox
| Chicago | Skype | ChicagoDF | ChicagoCU | Win10Mn | Win10V | Apps | Edge | Xbox_Platform
| Exchange15 | BitHum | O14QFE | Exchange15CU |  | Win10RS1
| Omain | Omain2 | O15 | ExchangeE16Ent |  | Win10RS2
| Onedrive | Sporel | O16 | ExchangeE19Ent |  | Win10RS3
| Onedrive2 |  | Omain2CCRel |  |  | Win10RS4
| Yammer |  | OMain2LTSB2018 |  |  | Win10RS5
|  |  | OmainCCRel |  |  | Win10Ti
|  |  | OmainCY18JulRel |  |  | OS
|  |  | OmainCY19JanRel |  |  | Store
OmainCY19JulRel
OmainLTSB2018
OmainCY20JanWin7
83 Enabled + Convert VCs (VC or Full) | 2020-02-06 | 2020-02-10 | 2020-02-13 | 2020-02-13 | 2020-02-26 | 2020-03-05 | 2020-03-11 | 2020-03-30 | 2020-04-20
Final LEAF Handback - Lionbridge | 2020-02-26: 2020-02-25; 2020-03-05: 2020-03-04; 2020-03-11: 2020-03-10; 2020-03-30: 2020-03-29; 2020-04-20: 2020-04-19
Switch Off Build Import | 2020-02-26: 2020-02-24; 2020-03-05: 2020-03-03; 2020-03-11: 2020-03-08; 2020-03-30: 2020-03-28; 2020-04-20: 2020-04-18
Inform Lionbridge & Moravia | 2020-02-04 | 2020-02-08 | 2020-02-11 | 2020-02-11 | 2020-02-21 | 2020-02-29 | 2020-03-05 | 2020-03-25 | 2020-04-15
83 Cultures DTT
83 Enabled + Convert VCs (VC or Full) | 2020-02-04: Monday
Final LEAF Handback - Lionbridge | 2020-02-04: Friday
Switch Off Build Import | 2020-02-04: Thursday
Inform Lionbridge & Moravia | 2020-02-04: Wednesday
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DTP Enabled and scheduled LCLExport also enabled on this Tenant...FreeFlow Tenant?

## Cultures
Language | OMain | Yammer | Chicago
Afrikaans | af-ZA | af-ZA | af
Amharic | am-ET | am-ET | am
Arabic | ar-SA | ar-SA | ar
Assamese | as-IN | as-IN | as-IN |  |  | be
Azerbaijani (Latin) | az-Latn-AZ | az-Latn-AZ | az-Latn-AZ |  | az | be-BY | az | be | 1
Bulgarian | bg-BG | bg-BG | bg |  |  | chr-Cher-US | bn-BD | be-BY | 19
Bengali (India) | bn-IN | bn-IN | bn-in |  | bn-BD |  | bs | chr-Cher-US | 1
Bosnian (Latin) | bs-Latn-BA | bs-Latn-BA | bs-Latn-BA |  | bs |  | pa-Arab-PK | ha-Latn-NG | 14
Catalan | ca-ES | ca-ES | ca |  |  |  | pl | hy-AM | 6
Valencian | ca-es-valencia | ca-es-valencia | ca-Es-VALENCIA |  |  |  | ga | hy | 6
Czech | cs-CZ | cs-CZ | cs |  |  |  | gd | ig-NG | 2
Welsh | cy-GB | cy-GB | cy |  |  |  | lb | ky-KG | 6
Danish | da-DK | da-DK | da |  |  |  | lo | ky | 6
German | de-DE | de-DE | de |  |  |  | mi | ku-Arab-IQ | 2
Greek | el-GR | el-GR | el |  |  |  | mt | mn-MN | 11
English (United Kingdom) | en-GB | en-GB | en-gb |  |  |  | ne | nso-ZA | 2
English | en-US | en-US | en-us |  |  |  | pa | prs | 6
Spanish | es-ES | es-ES | es |  |  |  | pl-PL | prs-AF | 5
Spanish (Mexico) | es-MX | es-MX | es-mx |  |  |  | quz | rw-RW | 2
Estonian | et-EE | et-EE | et |  |  |  |  | sd-Arab-PK | 11
Basque | eu-ES | eu-ES | eu |  |  |  |  | si-LK | 11
Persian | fa-IR | fa-IR | fa |  |  |  |  | sw | 5
Finnish | fi-FI | fi-FI | fi |  |  |  |  | sw-KE | 15
Filipino | fil-PH | fil-PH | fil |  |  |  |  | tg-Cyrl-TJ | 3
French (Canada) | fr-CA | fr-CA | fr-ca |  |  |  |  | ti-ET | 2
French | fr-FR | fr-FR | fr |  |  |  |  | tk-TM | 12
Irish | ga-IE | ga-IE | ga-IE |  | ga |  |  | tn-Za | 2
Scottish Gaelic | gd-gb | gd-gb | gd-gb |  | gd |  |  | uz | 5
Galician | gl-ES | gl-ES | gl |  |  |  |  | uz-Latn-UZ | 16
Gujarati | gu-IN | gu-IN | gu |  |  |  |  | wo-SN | 2
Hebrew | he-IL | he-IL | he |  |  | ha-Latn-NG |  | xh-ZA | 2
Hindi | hi-IN | hi-IN | hi |  |  | hy-AM |  | yo-NG | 2
Croatian | hr-HR | hr-HR | hr |  |  | hy |  | zu-ZA | 3
Hungarian | hu-HU | hu-HU | hu
Indonesian | id-ID | id-ID | id
Icelandic | is-IS | is-IS | is |  |  | ig-NG
Italian | it-IT | it-IT | it
Japanese | ja-JP | ja-JP | ja
Georgian | ka-GE | ka-GE | ka
Kazakh | kk-KZ | kk-KZ | kk
Khmer | km-KH | km-KH | km-KH
Kannada | kn-IN | kn-IN | kn |  |  | ky-KG
Konkani | kok-IN | kok-IN | kok
Korean | ko-KR | ko-KR | ko |  |  | ky
Luxembourgish | lb-LU | lb-LU | lb-LU |  | lb | ku-Arab-IQ
Lao | lo-LA | lo-LA | lo-la |  | lo
Lithuanian | lt-LT | lt-LT | lt |  |  | mn-MN
Latvian | lv-LV | lv-LV | lv
Maori | mi-NZ | mi-NZ | mi-NZ |  | mi
Macedonian | mk-MK | mk-MK | mk |  |  | nso-ZA
Malayalam | ml-IN | ml-IN | ml
Marathi | mr-IN | mr-IN | mr
Malay (Malaysia) | ms-MY | ms-MY | ms
Maltese | mt-MT | mt-MT | mt-MT |  | mt
Norwegian (Bokmål) | nb-NO | nb-NO | no |  |  | prs
Nepali | ne-NP | ne-NP | ne-NP |  | ne | prs-AF
Dutch | nl-NL | nl-NL | nl
Norwegian (Nynorsk) | nn-NO | nn-NO | nn-no |  |  | rw-RW
Odia | or-IN | or-IN | or |  |  | sd-Arab-PK
Punjabi (India) | pa-IN | pa-IN | pa-in | pa-Arab-PK | pa | si-LK
Polish | pl-PL | pl-PL | pl | pl | pl-PL | sw
Portuguese (Brazil) | pt-BR | pt-BR | pt |  |  | sw-KE
Portuguese (Portugal) | pt-PT | pt-PT | pt-pt |  |  | tg-Cyrl-TJ
Quechua | quz-PE | quz-PE | quz-PE |  | quz | ti-ET
Romanian | ro-RO | ro-RO | ro |  |  | tk-TM
Russian | ru-RU | ru-RU | ru |  |  | tn-Za
Slovak | sk-SK | sk-SK | sk |  |  | uz
Slovenian | sl-SI | sl-SI | sl |  |  | uz-Latn-UZ
Albanian | sq-AL | sq-AL | sq |  |  | wo-SN
Serbian (Cyrillic, Bosnia and Herzegovina) | sr-cyrl-ba | sr-cyrl-ba | sr-Cyrl-BA |  |  | xh-ZA
Serbian (Cyrillic, Serbia) | sr-Cyrl-RS | sr-Cyrl-RS | sr-cyrl |  |  | yo-NG
Serbian (Latin, Serbia) | sr-Latn-RS | sr-Latn-RS | sr |  |  | zu-ZA
Swedish | sv-SE | sv-SE | sv
Tamil | ta-IN | ta-IN | ta
Telugu | te-IN | te-IN | te
Thai | th-TH | th-TH | th
Turkish | tr-TR | tr-TR | tr
Tatar | tt-RU | tt-RU | tt
Uyghur | ug-cn | ug-cn | ug-cn
Ukrainian | uk-UA | uk-UA | uk
Urdu | ur-PK | ur-PK | ur
Vietnamese | vi-VN | vi-VN | vi
Chinese (Simplified) | zh-CN | zh-CN | zh-hans
Chinese (Traditional) | zh-TW | zh-TW | zh-hant

## Validation Rollout Schedule
Changes to Validation
Policheck and OSLEBot validation through SVS
We are dropping Fabric native code calling OSLEBot/Policheck and getting such results by calling SVS (Shared Validation Service) instead.
Validation results are identical and saved in Fabric in the same way. A minor difference is we now record the full OSLEBot rule name (i.e. Microsoft.Cerberus.Checks.CheckSize instead of CheckSize).
Tenants | Provisioned in SVS | Dark deployed in Fabric | In Prod in Fabric (tentative)
Omain | 2020-01-15 | 2020-01-16 | 2020-01-22
BitHum, Chicago, Exchange15, Omain, Omain2, Onedrive, Onedrive2, Sporel, Yammer | 2020-01-15 | 2020-01-16 | TBC
Skype, Win10Mn, Xbox_Platform | 2020-01-22 | 2020-01-23 | 2020-01-29
ChicagoCU, ChicagoDF, Exchange15CU, ExchangeE16Ent, ExchangeE19Ent, O14QFE, O15, O16, Omain2CCRel, OMain2LTSB2018, OmainCCRel, OmainCY18JulRel, OmainCY19JanRel, OmainCY19JulRel, OmainLTSB2018 | 2020-01-24 | 2020-01-27 | 2020-02-04
Apps, Edge, OS, Store, Win10Ti, Win10V | 2020-01-28 | 2020-01-29 | 2020-02-05
Win10RS1, Win10RS2, Win10RS3, Win10RS4, Win10RS5 | 2020-01-30 | 2020-01-31 | 2020-02-11
Games | 2020-02-10 | 2020-02-11 | 2020-02-18
C&AI tenants, list to be confirmed | tbc | tbc | tbc

## Build Import Sequence Schedule
Changes to Build Import sequence
We are making improvements to import builds in a more efficient and safe way.
We will now only process changed LCGs in any given build and will cache LCGs using FileService (owned by our team) to access them more efficiently once we retrieved them from the build drop. We have split the parsing of an LCG, the detection of changed resources, and the writing of changes in Fabric db into separate steps.
And we’re collecting metrics about the churn introduced in a build (count of resources added, updated, deleted, undeleted), introducing a new feature that will detect anomalous imports and pause them until it is confirmed that build is a valid one (and import can resume) or a rogue one (and import is abandoned).
Tentative schedule, week starting on:
1/13: Exchange15, Onedrive, Chicago, BITHum
1/20: Onedrive2, Yammer, Sporel, Apps
1/27: Azure, Systemcenter, Dynamics, Dynamics-AI, DynamicsBCSE
2/3 : Omain, Omain2 (note Omain :mso will be done last)
2/10: Remaining Windows tenants
2/17: Remaining Office tenants (includes Skype) + Dynamics, MSHealth, ICE
2/24: Remaining C&AI tenants

## Sheet2 (hidden)
Engineering Status
Not Started
In Dev
In Test
Prod Ready
No SWE Ask

## Draft Content Supplier Act.
Area | SLIM Tasks - https://microsoft.sharepoint.com/teams/OISGPortal/SitePages/Supplier%20Services.aspx | Summary | DTT Flow / Model Mapping | Comment
Articles W​orkflows​ | Articles PreHandoff workflow & documentation | iCMS Project Management and pre-HO file status monitoring | Pre-DTT Task but Open Question on R&R in DTT Model. Who creates / manages icms projects, their settings and files that are not assigned to any project | Open Question
| Articles HT Handoff workflow & documentation | Get list of all LocFiles which have LocFileStatus set to ReadyForDownload to isolate specific SOC scope only | Covered by new DTT API calls for translation jobs | Covered - Basic DTT HO scenario
| Articles Translation workflow & documentation | Translation of downloaded articles in LSP loc system | Flow for translations | Supplier Internal
| Articles Recycling workflow & documentation | Recycling of downloaded and processed articles in LSP loc system. | Internal to Moravia. Only change will be the move to MTPE so reduced dependency on Supplier side MT | Supplier Internal Except for MTPE shift
| Articles Customization workflow & documentation | Modification(s) of target article which cannot be achieved by change of source article | Covered by Post translation Improvement Job Scenarion wonce accompanised by a ADO to track churn | Covered - Basic DTT Improvement Job Scenario
| Articles PreHB eng validation workflow & documentation | Automatic verification of localized article LocFiles right after Translation Workflow is completed to avoid various errors or fails | Internal to Supplier - No Impact. Can remain as is! | Supplier Internal
| Articles HT Handback workflow & documentation | LSP loc system automated upload of localized Article LocFiles | Covered by new DTT API calls for translation jobs | Covered - Basic DTT HB scenario
| Articles PostHandback eng validation workflow & documentation | The aim is to detect articles which are stuck at specific LocFileStatus although the status does not directly represent fail to avoid TAT delays | Post Handback LocStatus Validation and monitoring. Is it required in DTT Model outside of Support? | Open Question
| Articles Quality Testing workflow & documentation | Help integration testing monthly | Is it required by an engineering or translation vendor in DTT Model? | Open Question
| Articles Quality BugFixing workflow & documentation | Process of reviewing any reported issues (VSTS items), investigation of its root cause and performing necessary steps for issue solving with an emphasis on priority of the issue | Needs to merge into the 'Improvement Job' scenario, so process, bug template, etc changes will be required. | Open Question
| Articles Quality (validation bugfixing) VaaS workflow & documentation | Automated validation checks (VaaS) run on SOC content. LSP consuming the data, categorize and fix issues. | This will move to the review job for all content for Policheck and non-Policheck will not be actioned until an updated validation plan is defined. | Covered in the Review Job for Policheck
| Articles Publishing (HighProfile content live rendering checks) workflow & documentation | HighProfile Articles content live rendering checks if requested as part of specific priority tasks (e.g. Ignite content | Post-DTT Task but Open Question on whether it is needed going forwards and R&R. | Open Question
| Articles OnePolicheck workflow & documentation | LSP performs regular Policheck reviews on all content handed back to iCMS | Covered by the revised Policheck Review DTT Jobs. | Covered in the Review Job for Policheck
Articles LQA workflow & documentation [Obsolete]
| Articles GTC and adhoc changes workflow & documentation | LSP ensures implementation of Global terminology changes and ad hoc changes requested by Language Moderators | Now manually triggered to the translation vendor as an Improvement Job | Covered as part of an Improvement Job
Articles Keywords (CHS only) workflow & documentation [Ob​solete]
| Articles LeftNavBars workflow & documentation | Letf navigation bars are special kind of support files which do not share same PreHO WF with Articles. Because of the special initialization phase (necessary to hand off new LeftNavBars) the process is about identification of new files, approval of their processing and after approval requesting iCMS indexing | May still be valid. Needs further review. Not DTT specific issue, but management and R&R an issue | Open Question
| Articles Reporting workflow & documentation | Moravia provides project health reports based on agreed SLAs, KPIs and metrics across all the pipes | DTT will bring a different loc pipe flow and expectation is that these will break. We should move to internally generated reports independent of supplier | Open Question
Articles CSH & Fallbacks (DHR support task) workflow & documentation [Ob​solete]
| Articles Special tasks - sample files localization workflow & documentation​ | Localization and engineering of sample files located on SOC sites | Who will own this task and process?? | Open Question (Process)
| Articles SME documentation​ | Taking care of high profile and complex tasks, which require deeper iCMS WFs and MAX knowledge. Supervising SWE bugs related to Service Alerts, checking iCMS Support resolutions and escalating in case issues are detected. Supporting internal team with regards to iCMS WFs, iCMS project setup or MAX authoring and following up where necessary. Suggesting, discussing, cooperating on and supporting WFs changes and optimizations or feature requests. | Needs to be internalised. | Open Question
| Articles (ULP, Collaterals, Ad hoc tasks) workflow & documentation | Localization and engineering of ULP requests, Collaterals or any other ad hoc tasks | Needs to be internalised. | Open Question
​Newsroom (Posts) W​orkflows​ | Newsroom PreHandoff workflow & documentation | Working with content writers, check notifications about new posts, VSTS task management, upload files via iCMS translation services | Why does newsroom need such extra focus ? Can we just set them as a higher priority even though they already have a 48 hr SLA | Open Question
| Newsroom Handoff workflow & documentation​ | SP system running automated query based on LAP method. | Covered by new DTT API calls for translation jobs | Covered - Basic DTT HO scenario
| Newsroom Translation workflow & documentation | Translation of downloaded articles in LSP loc system | Flow for translations | Supplier Internal
| Newsroom PreHandback workflow & documentation | Verify that the files are localized and localize links within the post. | Flow for translations | Supplier Internal
| Newsroom Publish workflow & documentation | Publishing translated files to MS Answers community, using localized arts if available, locking and pinning the posts. | Who will own this task and process?? | Open Question (Process)
| Newsroom PostHB workflow & documentation | Checking and editing the formatting of posts published to MS Answers community. Validating link functionality. | Who will own this task and process?? | Open Question (Process)
| Newsroom SQL Data Entry workflow & documentation | Gathering data of localized posts and running SQL query. | Who will own this task and process?? | Open Question (Process)
| Newsroom Policheck workflow & documentation | LSP performs regular Policheck reviews on all content handed back outside iCMS. | What 'non-icms' files are scanned? Why is it not part of the iCMS Scans? Who will own this task and process?? | Open Question (Process)
| Newsroom Reporting workflow & documentation | Moravia provides project health reports based on agreed SLAs, KPIs and metrics across all the pipes | DTT will bring a different loc pipe flow and expectation is that these will break. We should move to internally generated reports independent of supplier | Open Question
Art W​orkflows​ | Art Handoff workflow & documentation | LSP system running automated query based on LAP method | Will be covered by new DTT API calls for translation and Art review jobs | Covered - Basic DTT HO scenarios for Art (HT & MATUA)
| Art MATUA Review workflow & documentation | Review done on all MATUA arts retrieved via LAP which is performed by translators. cceptable arts are directly handed-back and published to Live site. The rest are sent to HT localization. The main purpose of the review is to determine if an art piece is of a good enough quality to be published live as is, or needs editing to improve the translation or layout | Scope increased significantly by the iCMS Art EOL management investments (EOL now internally automated). Supplier review process will remain as is, but DTT job will pre-decide and provide supplier with the approapriate fallback (HT or EN) for a failure. | DTT Jobs for MATUA Art. Review Process as is.
| Art MATUA HT Uplift workflow & documentation | The main purpose of this check is to make sure that there isn’t any HT article with MATUA FAIL arts | EOL is managed internally based on the article priority at the time. Retrospective uplift of art months later adds no value. This should be stopped. | Open Question (Process)
| Art Pre-Processing workflow & documentation | All arts intended for HT localization are going through the phase which assures that each art is categorized and that further steps in art processing are determined | Supplier internal but art categorization is interesting data (.PSD needed, Categorisation, Non-Loc) which we want returned to us as part of the cost accountability effort. | Supplier Internal Data that we need returned as part of the DTT Job
| Art Translation workflow & documentation | Translation of created art metafiles in LSP loc system. | Internal to Supplier. | Supplier Internal
| ​Art Recycling workflow & documentation | Recycling of created and processed art metafiles in LSP loc system. | Internal to Supplier. | Supplier Internal
| Art Customization workflow & documentation | Process of implementation of requested customizations. | This should be completed as part of an Improvement Job (Post translation / Bug Fix) | Covered - Improvement Job
| Art Post-Processing workflow & documentation | This phase serves completion of all DTP work performed on arts that have been processed through HT localization. | Internal to Supplier. | Supplier Internal
| Art PreHandback eng validation workflow & documentation | validation which runs on a specific scope of arts and verifies whether art metafile contains any undesirable keyword from the defined list in config file. | Internal to Supplier. | Supplier Internal
| Art Handback workflow & documentation | LSP loc system automated upload of Art LocFiles with internal status ReadyForHandback to LAP/iCMS. Potential HB errors are logged and actioned if applicable. | Covered by new DTT API calls for translation & Review Art jobs | Covered - Basic DTT HB scenario
| Art PostHandback eng validation workflow & documentation | Validation which runs on a specific scope of arts and compares handed-back version of art in LSP system with the one downloaded from the Live site using CRC. Validation ends by sending a report. | Retrospective Loc Art check. Support should monitor for checkin / publish failures. This should be stopped. | Open Question (Process)
| Art Quality BugFixing workflow & documentation | Process of reviewing any reported issues (VSTS items), investigation of their root cause and performing necessary steps for issue solving with an emphasis on priority of the issue | Now manually triggered to the translation vendor as an Improvement Job | Covered as part of an Improvement Job
| Art Policheck workflow & documentation | LSP performs regular Policheck reviews on all content handed back outside iCMS (e.g. localized art metafiles that are not handed back to iCMS ) | Who will own this task and process? Should this be internal | Open Question (Process)
| Art GTC and ad hoc changes​ workflow & documentation | LSP ensures implementation of Global terminology changes and ad hoc changes requested by Language Moderators into UA content | Now manually triggered to the translation vendor as an Improvement Job | Covered as part of an Improvement Job
| Art Reporting workflow & documentation | Moravia provides project health reports based on agreed SLAs, KPIs and metrics across all the pipes. | DTT will bring a different loc pipe flow and expectation is that these will break. We should move to internally generated reports independent of supplier | Open Question
Multimedia W​orkflows​ | Multimedia PreHandoff workflow​ & documentation​ | This process covers all actions that take place before Handoff in the Multimedia space. | Pre-DTT Task but Open Question on R&R in DTT Model. Who creates / manages icms projects, their settings and files that are not assigned to any project Going forwards Video EOL Management will be automated and not set manually against the project aligning with Art | Open Question on iCMS Project Owner and unassigned source files.
| Multimedia Handoff ​workflow​ & ​documentation​​ | This process covers handoff of Multimedia content and all actions that take place immediately after content is handed off. | * Validate files and iCMS project Settings - Who should own this and is it necessary * performing video content analyses required for capturing and narrating, - Supplier Internal * downloading video project files from RedTiger - Should this be automated?? | Video EOL will be automated. Video DTT Jobs will be enabled for HO & HB. Open Question - Should we provide Project files?
| Multimedia PreProcessing workflow & documentation​ | Process of preparing files for translation. Checking completeness of source files, modifying it for translation and sending it into translators | Internal to Supplier as part of the translation flow. | Supplier Internal
| Multimedia Translation workflow & documentation​ | Translation of downloaded video content in LSP loc system | Multimedia and text Loc will be decoupled so this should not be needed. EOL management of video will be in iCMS. Support should validate that no content gets blocked but apart from that the content should just flow based on the Due Date. Supplier process should no longer be needed | Process should not be needed in DTT job based model
| Multimedia Video content recycling workflow​ & documentation | Recycling of downloaded and processed articles and video content (Video Captions, Video Metadata, On Screen texts, Sample files, texts for images) in LSP loc system | MT and recycling of non binary multimedia files is coming to iCMS in Q3. This will make some of this process obselete, but otherwise this will be an internal supplier process | Process should not be needed in DTT job based model
| Multimedia CC post-processing workflow & documentation | The process describes adjustments that are made to Closed Caption (CC) files after localization | Internal to Supplier as part of the translation flow. | Supplier Internal
| Multimedia Full-loc video loc workflow & documentation | This process covers creation of fully localized video | Internal to Supplier as part of the translation flow. | Supplier Internal
| Multimedia TTS voice over video loc workflow & documentation | This process covers creation of ENU video with fully localized audio | Added Voice Over Localisation as a Video Loc Treatment option for Q3 Video investments. Otherwise internal to Supplier as part of the translation flow. | Supplier Internal
| Multimedia NewTasty video loc workflow & documentation​ | This process covers creation of fully localized video with no narration | Added Tasty Localisation as a Video Loc Treatment option for Q3 Video investments. Otherwise internal to Supplier as part of the translation flow. | Supplier Internal
| Multimedia PreHB eng validation workflow​ & documentation | This process describes validations that are run either manually or automatically before HBs. | Internal to Supplier as part of the translation flow. | Supplier Internal
| Multimedia Handback workflow​ & documentation​ | This process describes handback effort of localized files delivered back to MS | Covered by new DTT API calls for translation jobs. No longer need to track the full article family as iCMS will manage the chunking of localisation work. | Covered - Basic DTT HB scenario
| Multimedia Publishing workflow​ & documentation | The process ensures that all successfully localized files were HB, checked into the ICMS system and published properly for INTL markets. | Has some interesting TAT data which DTT needs investment to support. Should look for TAT clarification. Updated scenario to capture this requirement | Open Question
| Multimedia Quality workflow & documentation​ | The process describes quality assurance of already delivered content via live spot checks and the Validation tool | No Longer Valid. Should internal monitoring identify issues then they should be addressed as Improvement Jobs. Who drives live site monitoring internally. | Open Question
| Multimedia One Policheck workflow & documentation​ | LSP performs regular Policheck reviews on all content handed back to iCMS | Covered by the revised Policheck Review DTT Jobs. | Covered in the Review Job for Policheck
| Multimedia GTC and ad-hoc changes workflow​ & documentation​ | LSP ensures implementation of Global terminology changes and ad hoc changes requested by Language Moderators into UA content | Now manually triggered to the translation vendor as an Improvement Job | Covered as part of an Improvement Job
| Multimedia CheatSheet workflow​ & ​documentation | This process covers localization of Office cheat sheets and its updates. | Non - iCMS / Download Center based content. Is this still a valid scenario and how does it get localised in a DTT flow? | Open Question
| Multimedia Poster localization workflow & documentation | This process covers localization of Roadmap posters and its updates | Non - iCMS / Download Center based content. Is this still a valid scenario and how does it get localised in a DTT flow? | Open Question
| Multimedia Reporting workflow & documentation​ | Moravia provides project health reports based on agreed SLAs, KPIs and metrics across all the pipes. | DTT will bring a different loc pipe flow and expectation is that these will break. We should move to internally generated reports independent of supplier | Open Question
| Multimedia Special and other tasks, ad-hoc requests, production support workflow & ​documentation​​ | LSXPM requests new activity or specific production task through VSTS task that might result into logging new SAR to BPO for approval. | Now manually triggered to the translation vendor as an Improvement Job & ADO task | Covered as part of an Improvement Job
| Multimedia SME ​documentation​ | Taking care of new complex or ad hoc tasks, which requires iCMS/vCMS/MAX knowledge. Cooperating with iCMS/MAX/SWE teams on WFs optimization. Supervising, supporting internal team to adapt new processes into actual ones | Needs to be internalised. | Open Question
| Multimedia LQA workflow​ & documentation​ [Obsolete] | As per SOC and Newsroom | As per SOC and Newsroom | As per SOC and Newsroom
Multimedia LinkedIn specific localization ​workflow​​ & ​documentation [Obsolete]
TechCon W​orkflows​ | TechCon High Level workflow​
TechCon Content Selection workflow & documentation
DevPortals Content Selection workflow & documentation​
TechCon PreHandoff (Centers) workflow & documentation [Obsolete]
TechCon PreHandoff (DevDocs) workflow ​& documentation [Obsolete]
TechCon Prehandoff iCMS (New content set) workflow & documentation
​​TechCon & DevPortals HT Handoff (iCMS) workflow & documentation​
DevPortals HT Handoff (Compass Studio) workflow & documentation​
TechCon & DevPortals HT Translation workflow ​& documentation
​TechCon & DevPortals Articles Recycling workflow & documentation​
​​TechCon & DevPortals Pre​HB ENG Validation workf​low & documentation​
TechCon & DevPortals Handback (iCMS) workflow & documentation ​
TechCon ​Handback (Centers/DevDocs DxStudio) workflow & documentation [Obsolete]
DevPortals Handback (UHF) workflow & documentation​
DevPortals Validation (post HB) workflow & documentation​​​
TechCon & DevPortals ​Validation (Testing) workflow & documentation​
TechCon Validation (Vaas) workflow & documentation​
​TechCon & DevPortals Bugfixing workflow & documentation
TechCon Publishing workflow & documentation [Obsolete]
TechCon & DevPortals OnePolicheck workflow & documentation
TechCon & DevPortals LQA workflow & documentation [Obsolete]​
TechCon GTC and Ad-hoc changes workflow & documentation
TechCon Migration Conversion from DDUEML to MD workflow & documentation [Obsolete]
TechCon Migration Bugfixing and BB seeding workflow ​& documentation [Obsolete]
TechCon Migration Testing on staging workflow & documentation [Obsolete]
TechCon Migration Publishing to live workflow & documentation [Obsolete]​
TechCon Reporting workflow & documentation
TechCon & DevPortals Ad-hoc or Special requests workflow ​& documentation​
​​Templates W​orkflows​ | Templates Content Selection workflow & documentation
Templates PreHandoff workflow & documentation
Templates Handoff workflow & documentation
Templates PreProcessing workflow & documentation
Templates Translation workflow & documentation
Templates Translation Recycling workflow & documentation​​
Templates PostProcessing Customization workflow & documentation
Templates PreHandback eng validation workflow & documentation
Templates HandBack workflow & documentation
Templates PostHandBack eng validation workflow & documentation
Templates Quality workflow & documentation
Templates Publishing workflow & documentation
Templates OnePolicheck workflow & documentation
Templates LQA workflow & documentation [Obsolete]
Templates GTC changes workflow & documentation
Templates Reporting workflow & documentation​
Templates AdHoc TCMS tasks workflow & documentation
​High Speed Translations ​ | ​High Speed Translations​​ workflow & documentation | Mediation of conversation between end-users and MS representatives on answers.microsoft.com in end-user’s native language. | Who will own this task and process?? Seems to be outside iCMS | Open Question (Process)
Office Insider | Office Insider workflow & documentation | Localization and engineering of Office Insider website | Who will own this task and process?? Elena & Kathy work on these end points using manual compass Loc Seems to be outside iCMS | Open Question (Process)
PMG Workflows and Documentation | Homepage workflow | Homepage Flow for Supplier | Needs further clarification as flow is vague. How will PMG fit into a DTT job model. | Open Question (Process)
| Pricing workflow​ | Pricing flow | Needs further clarification as flow is vague. How will PMG fit into a DTT job model. | Open Question (Process)
| High priority issue workflow | Urgent Translation | Needs further clarification as flow is vague. How will PMG fit into a DTT job model. | Open Question (Process)
| Token management workflow​ | Token Management | Needs further clarification as flow is vague. How will PMG fit into a DTT job model. | Open Question (Process)